## Introduction
BETACODES - Integrated Risk Register & Executive Dashboard
ISO/IEC 27001:2022 & ISO 9001:2015 - Integrated Management System
DOCUMENT INFORMATION
Client | BETACODES
Project | ISO/IEC 27001:2022 & ISO 9001:2015 Compliance
Document Owner | BETACODES
Document Title | BETACODES-REGISTER-01 - Risk Register V1.1
Document Number | BETACODES-REGISTER-01
Version No | V 1.1
Classification | Confidential
WORKBOOK STRUCTURE
Executive Dashboard | Client-facing one-page view. 6 KPIs, 3 charts, 2 filters. Read-only in practice - edit nothing here except the two filter dropdowns.
Risk Register | The single source of truth. Type risks here. White cells are inputs; grey italic cells are calculated - do not overwrite them.
Dashboard Data | Live SUMIFS / COUNTIFS engine feeding the charts. No PivotTables, so nothing needs refreshing.
Lookup Lists | Governed dropdown lists and the risk-criteria parameters. Yellow cells are policy settings.
HOW TO USE
1. Add a risk by typing in the row directly under the last row of the register - the table extends itself and every calculated column fills down automatically.
2. A half-finished row is safe. Every calculated column returns blank until Ref is filled in, so no error can reach the dashboard.
3. All dropdowns read the Lookup Lists sheet. To add a category, owner or status, add it there first (insert a row INSIDE the list, not below it).
4. Risk banding is controlled by the yellow parameter cells on Lookup Lists. Change 18 to 12 and the whole register re-bands instantly - no formula edits.
5. The dashboard has no refresh step. It is built on live formulas, not PivotTables, so it updates the moment the register changes.
6. Overdue and review-due logic uses TODAY(), so the dashboard ages by itself between reviews.
RISK SCORING METHOD
Asset Value = C x I x A (each rated 1-3, so 1-27)
Asset Criticality = 1 if Asset Value <= 6, 2 if <= 12, 3 otherwise
Risk Score = Asset Criticality x Likelihood Score x Consequence Score (1-27)
Risk Level = HIGH if score >= 18, MEDIUM if >= 7, otherwise LOW (thresholds on Lookup Lists)
Post-Treatment Risk Score uses the same formula with the re-assessed likelihood and consequence.
Next Review Date = treatment date + 3 / 6 / 12 months depending on residual risk level (ISO 27001 Cl. 8.2).
CHANGES APPLIED IN V1.1
Asset Category standardised to the six governed values; the self-referencing dropdown was replaced with a Lookup Lists source.
Blank/partial row deleted and every calculated column made blank-safe, removing the errors that were breaking Risk Reduction %.
Corrupted Domain text in the Security Monitoring row repaired.
Treatment Action Timescale converted from text to true dates, enabling overdue and review logic.
Composite owners ('HR Manager / Compliance Consultant') reduced to one accountable owner each - review and adjust if the accountability sits elsewhere.
Nested IF score lookups replaced with MATCH against governed scales; risk thresholds and review intervals moved to parameter cells.
Five columns added: Risk Reduction %, Priority, Delivery Status, Next Review Date, Review Status. One hidden helper column, Dash Rank, drives the Top 5 chart.
DOCUMENT CHANGE RECORD
Version |  | Date | Updated By | Approved By
V 1.0 |  | 2026-06-26 | Ali Afzal (Compliance Consultant) | Waqar Ali (CEO)
V 1.1 |  | 2026-08-05 | Compliance Consultant | Pending

## Risk Register
RISK DESCRIPTION | [20 empty] | TREATMENT PLAN | [7 empty] | POST-TREATMENT ASSESSMENT | [6 empty] | DASHBOARD
Ref | Asset Category | Domain | Asset | Asset Description | Risk Description | Risk Type | Vulnerability | C | I | A | Asset Value | Asset Criticality / Rating | Asset Evaluation | Risk Owner | Likelihood | Likelihood Score | Likelihood Rationale | Consequences | Consequence Score | Consequences Rationale | Risk Score | Risk Value | Treatment Option Chosen | Proposed Treatment Action | Annex A/Control(ISO-27001 and ISO 9001 Standard) | Treatment Action Owner | Treatment Action Timescale | Treatment Action Status | Post Treatment Asset Value | Post-Treatment Likelihood | Post-Treatment Likelihood Score | Post-Treatment Consequences | Post-Treatment Consequences Score | Post-Treatment Risk Score | Post-Treatment Risk Level | Comments | Dash Rank
1 | HR | Human Resources / People Security | Human Resource (Employees) | Company personnel who access and process organizational and client information. | Employees are onboarded without background verification, creating exposure to insider threats, fraud, identity misrepresentation, and untrustworthy personnel handling sensitive data. | People | No background / pre-employment verification process performed during hiring. | 3 | 2 | 2 | 12 | 2 | MEDIUM | HR Manager | Likely | 2 | Without any screening control, the likelihood of onboarding an unverified or high-risk individual is high. | High | 3 | An unscreened insider with access to confidential information could cause serious harm to operations, reputation and clients. | 12 | MEDIUM | Modify | Background Verification process introduced. A Background Verification Form is completed for each employee and verification is performed after collection of the required data. | ISO 27001:2022 - A.6.1 Screening; A.6.2 Terms and conditions of employment. ¦ ISO 9001:2015 - Cl. 7.1.2 People; Cl. 7.2 Competence. | HR Manager | 2026-06-29 | Close | 2 | Rare | 1 | Moderate | 2 | 4 | LOW | Close. Background Verification Forms completed and verification records maintained by HR. | 4
2 | HR | People Security / Competence & Awareness | Workforce (All Employees) | All staff required to understand their information security (ISMS) and quality (QMS) responsibilities. | No ISMS and Quality Management awareness training conducted; staff unaware of security and quality obligations, increasing human error, policy violations and nonconformities. | People | No information security and quality awareness / training program delivered to staff. | 2 | 2 | 2 | 8 | 2 | MEDIUM | HR Manager | Likely | 2 | Untrained staff are highly likely to make security and quality errors during day-to-day work. | High | 3 | Lack of awareness can lead to widespread errors, security incidents and quality nonconformities across the organization. | 12 | MEDIUM | Modify | ISMS and QMS awareness training conducted for all employees by the HR Manager and Compliance Consultant. Attendance and training records maintained. | ISO 27001:2022 - A.6.3 Information security awareness, education and training. ¦ ISO 9001:2015 - Cl. 7.2 Competence; Cl. 7.3 Awareness. | HR Manager | 2026-06-29 | Close | 2 | Rare | 1 | Moderate | 2 | 4 | LOW | Close. Combined ISMS & QMS awareness training session held on the 29th; attendance sheet retained as evidence. | 4
3 | Software and Application | Secure Software Development / Application | DataNext Application Source Code | Proprietary application source code developed and maintained by BETACODES. | Source code of DataNext released without a security code review; insecure coding, undetected vulnerabilities and quality defects may reach production. | Technology | No secure source-code review process within the software development life cycle. | 3 | 3 | 2 | 18 | 3 | HIGH | Development Lead | Likely | 2 | Without code review, vulnerabilities and defects are likely to remain undetected in delivered software. | High | 3 | Exploitable code flaws could lead to data compromise, service failure and loss of client confidence. | 18 | HIGH | Modify | Secure source-code review performed on the DataNext application by Development Leads and a code review report generated and retained. | ISO 27001:2022 - A.8.28 Secure coding; A.8.25 Secure development life cycle; A.8.29 Security testing in development and acceptance. ¦ ISO 9001:2015 - Cl. 8.3 Design and development; Cl. 8.5 Production and service provision. | Development Lead | 2026-06-26 | Close | 3 | Rare | 1 | Moderate | 2 | 6 | LOW | Close. Code review completed; review report generated and findings remediated. | 6
4 | Infrastructure | IT Infrastructure / Network Security | Network Servers | Production network servers hosting business and client-facing services. | No penetration testing performed on network servers; exploitable vulnerabilities and misconfigurations may remain undetected and be exploited by attackers. | Technology | Absence of periodic vulnerability assessment and penetration testing of servers. | 3 | 2 | 3 | 18 | 3 | HIGH | IT Head | Likely | 2 | Internet-facing/production servers without testing are likely to contain exploitable weaknesses. | High | 3 | A successful exploit could result in data breach, service downtime and severe operational and reputational impact. | 18 | HIGH | Modify | Penetration testing performed on network servers; identified findings remediated and the PT report retained. | ISO 27001:2022 - A.8.8 Management of technical vulnerabilities; A.8.29 Security testing; A.8.9 Configuration management. ¦ ISO 9001:2015 - Cl. 7.1.3 Infrastructure. | IT Head | 2026-06-29 | Close | 3 | Rare | 1 | Moderate | 2 | 6 | LOW | Close. Penetration test completed, findings remediated and verified. | 6.0001
5 | Infrastructure | Endpoint Security / IT Assets | Workstations / PCs (Endpoints) | Employee workstations used to access and process company and client data. | Anti-malware not uniformly installed across all endpoints (mix of open-source, Windows Defender, and unprotected devices); inconsistent protection leaves devices exposed to malware. | Technology | Inconsistent / missing endpoint anti-malware protection across PCs. | 2 | 2 | 2 | 8 | 2 | MEDIUM | IT Head | Likely | 2 | Unprotected or inconsistently protected endpoints are likely to be infected by malware. | High | 3 | Malware infection could spread across the network, causing data loss, downtime and compromise of client data. | 12 | MEDIUM | Modify | Endpoint anti-malware standardized and installed on all PCs (managed Windows Defender / approved solution). Coverage verified across the fleet. | ISO 27001:2022 - A.8.7 Protection against malware; A.8.1 User endpoint devices. ¦ ISO 9001:2015 - Cl. 7.1.3 Infrastructure. | IT Head | 2026-06-26 | Close | 2 | Rare | 1 | Moderate | 2 | 4 | LOW | Close. Anti-malware installed and confirmed active on all endpoints. | 4.0001
6 | Documentation (GRC) | Access Control / Identity & Access Management | User Access Management Records | Records that authorize, grant and track user access rights to systems and applications. | User access granted without formal authorization forms; risk of unauthorized or excessive access rights with no audit trail of access provisioning. | Technology | No formal user access request / authorization process and records. | 3 | 2 | 2 | 12 | 2 | MEDIUM | HR Manager | Likely | 2 | Without formal authorization, inappropriate or excessive access is likely to be granted and go unnoticed. | High | 3 | Excessive or unauthorized access could lead to confidentiality breaches and inability to demonstrate accountability. | 12 | MEDIUM | Modify | User Access Request/Authorization Forms created and completed for all users; access formally authorized and recorded. | ISO 27001:2022 - A.5.15 Access control; A.5.16 Identity management; A.5.18 Access rights; A.8.2 Privileged access rights. ¦ ISO 9001:2015 - Cl. 7.5 Documented information. | HR Manager | 2026-06-26 | Close | 2 | Rare | 1 | Moderate | 2 | 4 | LOW | Close. User access forms created and completed for all users; access register maintained. | 4.0001
7 | Documentation (GRC) | Governance / Management System Documentation | ISMS & QMS Documentation | Governance, policies, processes and procedures that direct the information security and quality management systems. | Absence of documented ISMS and QMS framework (governance, policies, processes, procedures) leading to inconsistent operations, non-compliance with ISO 27001 / ISO 9001 and audit failure. | Process | No documented management system framework established. | 2 | 3 | 2 | 12 | 2 | MEDIUM | Compliance Consultant | Likely | 2 | Without documented direction, inconsistent and non-conforming practices are highly likely. | High | 3 | Lack of documentation results in compliance failure, certification non-conformities and uncontrolled operations. | 12 | MEDIUM | Modify | Complete ISMS and QMS documentation set (governance framework, policies, processes and procedures) developed, approved and published by the Compliance Consultant. | ISO 27001:2022 - A.5.1 Policies for information security; Cl. 7.5 Documented information. ¦ ISO 9001:2015 - Cl. 4.4 QMS and its processes; Cl. 5.2 Policy; Cl. 7.5 Documented information. | Compliance Consultant | 2026-06-26 | Close | 2 | Rare | 1 | Moderate | 2 | 4 | LOW | Close. Full ISMS & QMS document set developed, approved and published. | 4.0001
8 | Miscellaneous | Asset Management | Asset Issuance Records / Inventory | Records of company assets issued to and returned by employees. | No records maintained for assets issued to employees; loss of accountability, untracked assets and potential loss or theft of equipment and the data they hold. | Process | No asset issuance form or inventory record-keeping in place. | 2 | 2 | 2 | 8 | 2 | MEDIUM | Operations Team | Likely | 2 | Without issuance records, untracked and unaccounted-for assets are likely. | Moderate | 2 | Lost accountability can lead to asset loss and exposure of data stored on the assets. | 8 | MEDIUM | Modify | Asset Issuance Forms created; issuance and return of assets recorded and maintained by the Operations team. | ISO 27001:2022 - A.5.9 Inventory of information and other associated assets; A.5.10 Acceptable use of assets; A.5.11 Return of assets. ¦ ISO 9001:2015 - Cl. 7.1.3 Infrastructure; Cl. 7.5 Documented information; Cl. 8.5.3 Property belonging to customers/external providers. | Operations Team | 2026-06-26 | Close | 2 | Rare | 1 | Slight | 1 | 2 | LOW | Close. Asset Issuance Forms created and issuance/return records maintained. | 2.0001
9 | Infrastructure | Backup / Business Continuity | Data Backups | Backup copies of critical business and client data. | No offsite backup location; a site-level incident (fire, theft, disaster) could destroy primary and backup data simultaneously, causing permanent data loss. | Technology | Backups stored only on-site with no geographic redundancy. | 2 | 3 | 3 | 18 | 3 | HIGH | IT Head | Likely | 2 | A single on-site copy is vulnerable to any localized incident affecting the primary site. | High | 3 | Simultaneous loss of primary and backup data would be catastrophic and likely unrecoverable. | 18 | HIGH | Modify | E11 office identified and established as the offsite backup location; backups replicated offsite and restoration successfully tested. | ISO 27001:2022 - A.8.13 Information backup; A.5.29 Information security during disruption; A.5.30 ICT readiness for business continuity; A.7.5 Protecting against physical and environmental threats. ¦ ISO 9001:2015 - Cl. 7.1.3 Infrastructure; Cl. 7.5.3 Control of documented information. | IT Head | 2026-06-26 | Close | 3 | Rare | 1 | Moderate | 2 | 6 | LOW | Close. Offsite backup at E11 established; backup replication and restoration test completed. | 6.0001
10 | Documentation (GRC) | Security Monitoring / Logging | Endpoint Devices & Logs | Endpoints and servers requiring security event logging and monitoring. | No tool for endpoint logging and monitoring; security events and incidents on devices go undetected, delaying detection and response to threats. | Technology | Absence of centralized logging and monitoring on endpoints/devices. | 2 | 3 | 2 | 12 | 2 | MEDIUM | IT Head | Likely | 2 | Without monitoring, malicious or anomalous activity is likely to go undetected. | High | 3 | Undetected incidents can escalate, increasing breach impact and response time. | 12 | MEDIUM | Modify | Wazuh deployed for centralized logging and monitoring of endpoints/devices; alerting and log review operational. | ISO 27001:2022 - A.8.16 Monitoring activities; A.8.15 Logging; A.5.7 Threat intelligence. ¦ ISO 9001:2015 - Cl. 9.1 Monitoring, measurement, analysis and evaluation. | IT Head | 2026-06-26 | Close | 2 | Rare | 1 | Moderate | 2 | 4 | LOW | Close. Wazuh implemented; devices onboarded for logging and monitoring. | 4.0001

## Dashboard Data
DASHBOARD DATA ENGINE
Every block below is live: it reads tblRiskRegister directly with SUMIFS / COUNTIFS and recalculates the instant a risk is added or edited. No refresh step exists.
Rows inside each block are listed in REVERSE display order - Excel plots the first category at the bottom of a horizontal bar chart.
FILTER CRITERIA ("<>" means "any non-blank value", i.e. no filter)
Asset Category criterion | <>
Treatment Status criterion | <>
BLOCK 1 - Risk exposure by asset category > Chart 1 |  |  |  | BLOCK 3 - Top 5 residual risks > Chart 2
Asset Category | Inherent Exposure | Residual Exposure |  | Risk (Asset) | Residual Score
Miscellaneous | 8 | 2 |  | ISMS & QMS Documentation | 4
Peripherals (Devices) | 0 | 0 |  | Endpoint Devices & Logs | 4
Software and Application | 18 | 6 |  | DataNext Application Source Code | 6
HR | 24 | 8 |  | Network Servers | 6
Infrastructure | 48 | 16 |  | Data Backups | 6
Documentation (GRC) | 36 | 12
Ranking is driven by the hidden 'Dash Rank' column in the register, which respects both dashboard filters.
BLOCK 2 - Treatment delivery by accountable owner > Chart 3
Accountable Owner | Pending | Open | Close
Operations Team | 0 | 0 | 1
IT Head | 0 | 0 | 4
HR Manager | 0 | 0 | 3
Development Lead | 0 | 0 | 1
Compliance Consultant | 0 | 0 | 1

## Executive Dashboard
Enterprise Risk Management Dashboard |  |  |  |  | Last Updated: 14 Aug 2026 01:20
Live view - recalculates automatically. No refresh required.
ISO 27001:2022 ¦ ISO 9001:2015 ¦ Executive Risk Overview
ASSET CATEGORY |  |  | TREATMENT ACTION STATUS
All |  |  | All |  | Both filters drive every KPI and every chart on this page.
TOTAL RISKS IDENTIFIED | HIGH RESIDUAL RISKS | RISK REDUCTION |  | OPEN TREATMENT ACTIONS | OVERDUE ACTIONS | CLOSED TREATMENT ACTIONS | MEDIUM RESIDUAL RISKS | LOW RESIDUAL RISKS
10 | 0 | 67.16% |  | 0 | 0 | 10 | 0 | 10
Formulas:
OVERDUE ACTIONS = COUNTIFS(tblRiskRegister[Asset Category],CritCat,tblRiskRegister[Treatment Action Status],CritStatus,tblRiskRegister[Treatment Action Status],"<>Close",tblRiskRegister[Treatment Action Timescale],"<"&TODAY())

## Lookup Lists
Asset Category | Likelihood | Consequence | Treatment Action Status | Treatment Option | Owner / Accountable Role | Risk Criteria Parameter | Value | Category Filter | Status Filter
Documentation (GRC) | Rare | Slight | Pending | Avoid | Compliance Consultant | High risk threshold (score >=) | 18 | All | All
Infrastructure | Likely | Moderate | Open | Accept | Development Lead | Medium risk threshold (score >=) | 7 | Documentation (GRC) | Pending
HR | Almost Certain | High | Close | Modify | HR Manager | Review interval - HIGH (months) | 3 | Infrastructure | Open
Software and Application |  |  |  | Share | IT Head | Review interval - MEDIUM (months) | 6 | HR | Close
Peripherals (Devices) |  |  |  |  | Operations Team | Review interval - LOW (months) | 12 | Software and Application
Miscellaneous | [5 empty] | 'Due soon' window (days) | 30 | Peripherals (Devices)
Miscellaneous
Yellow cells are policy parameters.
Changing one re-bands the whole register instantly.
No formula anywhere hard-codes these numbers.
HOW TO EXTEND THESE LISTS
1. To add a value, right-click a row INSIDE the list (not the row below it) and Insert.
Inserting inside the range makes every defined name, dropdown and formula follow automatically.
2. Likelihood and Consequence are ORDERED lists - position in the list IS the score (row 1 = score 1).
Never reorder them without re-baselining the register.
3. Adding an Asset Category also needs one row inserted inside the Category Filter list (column P)
and inside the 'Exposure by Asset Category' block on the Dashboard Data sheet.
4. Adding an Owner also needs one row inserted inside the 'Delivery by Owner' block on Dashboard Data.